## Project Planner(Triller Sol)
Project Planner For CNX_Protect | [6 empty] | Period Highlight: | 30 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete
Activity | Plan Duration (Cumulative in weeks) | Order of Activities (Parallel/Series) | Grantt Chart Activities | Individual Activities timeline (in weeks ) | Actual Start | Actual Duration (in weeks) | Percentage Complete | Weeks
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Fundamental Infrastructure | 1 | 1 | 1 | 1 | 27/05/2021 | 27/05/2021 | 10% | bar: Weeks 2
Frontend User Credentials | 5 | 2 | 2 | 5 | 2021-04-06 | To be Started | 0% | bar: Weeks 2
Upload Files | 7 | 3 | 5 | 7 | 2021-02-07 | To be Started | 0%
Linkage with Production | 10 | 4 | 8 | 10 | 16/07/2021 | To be Started | 0%
| 12 | 5 | 13 | 12 | 2021-03-08 | To be Started | 0%
12
Results/Output
Total
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hardware and Software Requirement. Platform setup
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Creating authentication for new users by integriting with Microsoft365 account to signup. ALso, includes Sign-in and Sign-out for autherized users.
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Browser to upload the latest keyword file and updated folders for inputs
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Link with the main script for searching keywords.
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Save the generated reports in desired format for user workspace.